## Linear Regression
Linear Regression
Project | x | y | y* | xy | x^2 | y^2 | MRE | MRE% | PRED(0.25)
PRJ001 | 186 | 531 | 545.8462 | 98766 | 34596 | 281961 | 0.027959 | 2.7959 | x
PRJ002 | 335 | 415 | 426.5356 | 139025 | 112225 | 172225 | 0.027797 | 2.7797 | x
PRJ003 | 245 | 534 | 498.6024 | 130830 | 60025 | 285156 | 0.066288 | 6.6288 | x
PRJ004 | 227 | 504 | 513.0158 | 114408 | 51529 | 254016 | 0.017888 | 1.7888 | x
| 993 | 1984 | 1984 | 483029 | 258375 | 993358 | 0.034983 | 3.4983 | 1
Legend
X | size unit (FP, LOC, ...)
Y | effort in man/days
Y=c1+c0*X
n= | 4 |  | C0= | -0.80074 |  | C1= | 694.7842
S(xy) | 483029
S(x) | 993
S(y) | 1984
S(x^2) | 258375
S(x)^2 | 986049
New Project
Size (X)
Effort (Y) estim | 694.7842 | m/d
Note: in order to calculate the MRE, MMRE and Pred(0.25) for the new dataset:
1) insert a new row after PRJ004 project data
2) copy formulas from the the previous row
3) insert in the B column the new size and in the C column the estimated effort
Note on I9: MMRE
Note on B26: Insert the no. Of sizing units counted

## Exponential Regression
Exponential Regression
Project | x | y | log y | log y* | y* | xy | x^2 | y^2 | log y | xlog y | MRE | MRE% | PRED(0.25)
PRJ001 | 186 | 531 | 2.7251 | 2.7395 | 548.9376 | 98766 | 34596 | 281961 | 2.7251 | 506.8676 | 0.033781 | 3.3781 | x
PRJ002 | 335 | 415 | 2.618 | 2.6288 | 425.4354 | 139025 | 112225 | 172225 | 2.618 | 877.0461 | 0.025146 | 2.5146 | x
PRJ003 | 245 | 534 | 2.7275 | 2.6957 | 496.2414 | 130830 | 60025 | 285156 | 2.7275 | 668.2476 | 0.070709 | 7.0709 | x
PRJ004 | 227 | 504 | 2.7024 | 2.7091 | 511.7582 | 114408 | 51529 | 254016 | 2.7024 | 613.4517 | 0.015393 | 1.5393 | x
| 993 | 1984 | 10.7731 | 10.7731 | 1982.3726 | 483029 | 258375 | 993358 | 10.7731 | 2665.613 | 0.036257 | 3.6257 | 1
Legend
X | size unit (FP, LOC, ...)
Y | effort in man/days
d= | 0.99829 |  |  | Log d = | 0.003 | -0.00074288
c= | 754.569 |  |  | Log c = | 1.781 | 2.8777
Y=c+d^X
n= | 4 |  | Num1 | -35.2505
S(xy) | 483029 |  | Num2 | 136549.6942
S(x) | 993 |  | Den | 47451
S(y) | 1984
S(x^2) | 258375
S(x)^2 | 986049
Log y | 10.7731
xLogy | 2665.613
New Project
Size (X)
Effort (Y) estim | 755.569 | man/days
Note: in order to calculate the MRE, MMRE and Pred(0.25) for the new dataset:
1) insert a new row after PRJ004 project data
2) copy formulas from the the previous row
3) insert in the B column the new size and in the C column the estimated effort
Note on M9: MMRE
Note on B32: Insert the no. Of sizing units counted