Change As Seen From The Staff’s Perspective


Patient-Focused Care Efforts





Duke Rohe, Performance Improvement and some help from the Pritchett books








Results of Our Change on Acute Care Units


Cost per Stay reduced 13%


Patient Satisfaction jumped from the 50th percentile to the 80th percentile in a 400 hospital database


Physician Rounding efficiency doubled


The staff near unanimous about not returning to the old way


Staff are localized in tiny “substations in the hall” - closer to the patient


All paperwork is outside patient door


Every output is evaluated in terms of its patient-focus and customer-focus value


Cost of change: $35k for 30 bed unit and $600 per employee training





In The Beginning


Staff didn’t believe that whatever was put in place would stick.


There was a core of believers who were going to muster whatever it took to create a patient-focused environment.


Staff had a wait-and-see,  even skeptical attitude about the chances of success.


As the new way was being created, much of the hospital was doing business as usual.  Unaware that what was developing would have high impact on them.


Only a select number representing all of nursing and other departments could participate in the recommendations for changes.


Staff had to go through a detoxification process of realigning the job duties around the convenience and efficiency of the patient (process) rather than their own specialization.


Learned that there were a lot of duties that could be shared among departments.  Departments did not have a corner on the market of being the only one to do their specialty.  Reality struck that their future jobs may be doing something different.  Job security was threatened, however a pledge from the president to avoid all possible layoffs helped.


Six principles (vision) for decision making filtered the right actions.





Lessons Learned


Your approach to changing the culture should be out of character for the organization


Don’t try to sneak up on people with cultural change.  Be terribly obvious.


The worst thing you can do is sit a wring your hands.  The best way to predict the future is to invent it. Participate.


People will question organizational motives and approach, but this adds little value to the eventual change.


There must be a vision that holds their attention and hooks their heart.  Everything else falls in line once this is established.


Fear, doubt and resistance to change rush to fill in the vacuum when there is a breach in the vision.  Find it.








During the Pilot and Implementation Phases


All eyes were on the pilot unit, some hoping for the dawn of a new level of care, some skeptically doubting that anything would change - but were they wrong.


Jealousy arose because of the special treatment given to the pilot as plans were being developed to spread this process throughout.  It was hard to deal with, but it was a natural part of change.


Staff went through a fearful period as they learned to trust others in the new roles and they adjusted for the right fit.  There was some “grinding of gears” until the new process took hold. Ambiguity in roles were high.


We learned as we went, almost like feeling your way into the new process.   Learned we can’t expect the same staff to implement change, train new skills and deliver care at the same time.  Extra support was hired, but later transferred the position because the kinks had been worked out.


Staff that were not yet involved couldn’t get enough communication.  They were glad they didn’t have to blaze the first trail, but they were mad they didn’t have any input.  Organizational listening is a developmental process.  Eventually their input will be the ongoing part of change- considered and installed on an appropriate  (localized to a global) basis.


Had a communication video, monthly open forum (poorly attended) updates, weekly voicemail broadcast (helpful), articles in the hospital wide newsletter, voicemail line for ideas, questions and concerns.  (most grumbling happens underground).


Boy do the rumors have a field day.


Departments giving away traditional duties were resentful at first, but later supportive.


Cleaning rooms was a pride issue of Nursing.  There were a lot of threats to jump ship. Upper management firmly reinforced that these changes are for the patient, not the nurses. The exodus never materialized.


Staff were told this is the way we now care for patients- You need to make a decision if you are with us?


Staff were trained as teams to solve problems, support each other.  Some units were teachable, some were not.  A lot of the success had to do with the strength of the manager to push the change through.  Coordinated change is not a natural happening.


Change was difficult, but it has made the staff stronger for further changes.  You don’t make a change just to sit back and get passed by.





Lessons Learned


Bureaucracy is enemy number one.  So question everything.


You need tremendous communication to sustain culture change.


Nonstop communication is needed to offset ambiguity, counteract confusion, shift attitudes, and keep people on course.


Forming new job roles is like driving in a fog, you can only see a little way, but you can make the whole trip that way.


The new culture must be pursued, relentlessly.


Some people would rather delegate responsibility upward than endure a culture change.


You must insist on involvement; mobilize everyone.  The whole organization should be buzzing.


Just as your behavior influences the actions of others, the spirit with which you do it colors their attitude.


Don’t give up.  If you look from a hilltop at a swimmer going across a lake, you may see that he is half way  from his starting point.  To the swimmer the distance in the middle of the lake looks the same as when he took his first strokes.  He never looks back so he forgets where he has come from.  Change works like that.  In order not to get discouraged, look back at where you came from to give you perspective.  You may be closer to the finish line than you think.








After implementation


When consulting with other hospitals, staff will admit their disagreement, reluctance, and apprehension with the change.  But they state they will not go back to the old ways.


Staff are now warning academia that what you are taught in school is lagging behind reality.


Staff are quick to find solutions, quick to consider the global decision of things, ready for the next change.  It is not a matter of if, but of when.


Making bigger changes faster.  More customer focus: of patients, family members, of physicians, of fellow staff members , of the process.





Lessons Learned


Culture change is like going in for surgery-- nobody does it for the thrills


The existing culture can not tolerate the unconventional


The good reason for high-velocity culture change; there are no valid arguments for going slow


Speed may scare you, but lack of speed is what let problems get out of hand./xoldstuff/uasaa


