Free Wheel

Relawan kemanusiaan untuk korban Tsunami

The MISSION

The realization of Solidarity of the country and solidarity of the family to helps the survivors after the Tsunami .

With the evaquation to the survivors and put them to the safe area, make them to recovery in health and traumatic.

The following are job requirement to  make the job done .

Letters requirement.

1. OPS-Letters for Plane operation at Aceh to the Transport Minister.

2. OPS Free Wheel

3. Letter to the Pertamina to request the fuel at Aceh

Members

1. Tim Medis & Paramedis 
= 21 orang

2. Tim Komunikasi
=   3 orang

3. Tim Wanadri
= 10 orang

4. Koordinator
=   3 orang

Total
= 57 orang

Cargo :

1. Obat-obatan 
= +/- 3 ton

2. Alat-alat komunikasi

3. Perahu Karet 
= 5 buah berikut mesin

4. Bekal Tim

5. Tenda 

Supports

1. Flight POLRI

2. Airforce Flight plot for RCTI which will be swith to Us

3. Pesawat Airvan Kaltim 
= 2 unit

4. Pesawat Airvan Australia 
= 2 unit on the next 2 weeks

5. Truk IMBI Medan 
= 2 unit

6. Kapal Laut (AL)

7. Satelit Telepon 
= 2 unit (borrowing)

Free Wheel

Relawan kemanusiaan untuk korban Tsunami

Schedule

Thursday 6 jan 2005

1. Obat-obatan + Cargo sudah di Ampera

2. Daftar Nama, ID Card

3. Perencanaan :

a. Akomodasi, Transportasi, Logistic (Bekal Tim), Pendanaan.

b. Susun organisasi, Pembagian Tugas.

c. Posko Utama, Poskotis

d. SOP

e. Komunikasi

f. Transportasi :
Darat 
- truk dari IMBI Medan


Udara
- Pol. Udara (F50)



-  RCTI (737)



- Kapolda Metro?



- Com. Flite

4.  Coordination meeting  at 14.00

a. Full Team

b. Frans Wenas

c. Soen

Friday 7 Jan 2005

· 10  Doctors fligh etd 7.00 dari Cengkareng depart to Blah Bintang – Banda Aceh

· 10 Doctors Airforce flight from Halim Perdana Kusumah to Bandara Blah Bintang-Banda Aceh

· 10 personal by POLRI Flight at 10.00 fom Pondok Cabe Airport to Balh Bintang – Banda Aceh

· Poskot  – Comuniction , Posko, Personalia, Distribution

· Scheduling and Placement

datel 6 – 20Jan 2005 OPS Office Free Wheel

· Follow up the requirement at site

· Supply the needs

· Replacement plan

PAGE  
1

