Clandersville International Outdoor Music Festival

Report for Mayor Trino’s Office

September 25, 2006

Submitted by the C.I.O.M.F. Organizers

Contact Person: Willem Lester

Draft 1

Welcome

Introduction

This year Clandersville made its mark on the music XE "music"  festival XE "festival"  map with the first annual Clandersville International Outdoor Music Festival (C.I.O.M.F.). We organized our first annual international music festival, held in the beautiful River View Park. 

The festival XE "festival"  took a lot of work and planning. We got the idea for the event nearly a year ago and realized that we needed to begin planning pretty soon if we wanted it to happen. We started brainstorming and drafting plans. John Yucca and Marla Jones have contacts in the music XE "music"  world and managed to come up with a list of international musicians XE "musicians" . 

Then we needed to find a site, line up musicians XE "musicians" , coordinate their travel, coordinate vendors XE "vendors" , schedule the lineup, develop an area and activities for children, get sound equipment, get all the various permits, plan the traffic flow, and ensure clean-up afterwards.

While the festival XE "festival"  took a lot of work and planning, we certainly learned a lot along the way. In this report, you will find some of the information you need to make this festival a successful annual event. Mayor Trino asked us to draft a report to help future festival planners. While this report is by no means exhaustive, we hope you find it helpful.

Gratitude

We could not have made this festival XE "festival"  such a great success without the help of countless volunteers, musicians XE "musicians" , the Clandersville Arts Council, Mayer Trino and her  wonderful staff, and all the people of Clandersville and the surrounding region who came out and supported us for all three days. Thanks also to the Parks Office for helping with the camping facilities. 

Table of Contents

Bands

Introduction

In our planning meetings, we thought carefully about what kind of music XE "music"  we wanted. We wanted all of it, frankly—we wanted the sounds of instruments and voices from Africa, South America, Scandinavia, Eastern Europe, India, and so on. We wanted steel drums from Trinidad, fado from Portugal, throat-singing from Tuva. We envisioned a lineup that included Norwegian pop, Gaelic seisuns, and Nigerian Afrobeat. 

We considered how many stages we could have (one major, two minor) and how many musicians XE "musicians"  could play on each stage per day. We also had to plan how we wanted to organize the lineup.

With all of this in mind, we contacted musicians XE "musicians"  and bands from all over the world. We were aware that many would not be able to play at our festival XE "festival" , so we had a back-up list of other musicians and bands XE "bands" \t "See musicians"  that we wanted. 

We used local travel agency Travel-a-Go-Go to help some of the musicians XE "musicians"  plan their trips to Clandersville. Other musicians preferred to take care of these arrangements themselves. 

Lineup

We had a terrific number of musicians XE "musicians"  from all over the world. While we would be delighted if all the musicians could return each year, we know that many have other scheduling/tour plans. Also, we want to recognize diverse talents, including up-and-coming musicians as well as those unable to make it to Clandersville this year.

Due to political situations, some musicians XE "musicians"  were unable to travel here to perform in this year’s festival XE "festival" , but we would certainly like to keep them in mind for next year. 

Recommendations

For next year, we might consider a shuttle bus to the airport. We would also suggest trying a system of “host families” to house some of the less well-known musicians XE "musicians" . Also, we hope to get more vendors XE "vendors"  to sponsor the musicians’ travel.

Sponsors and Support

Introduction

We explained the festival XE "festival"  idea to a number of local businesses, nearly all of whom were happy to contribute in exchange for signage at the festival. Even the signs were contributed! We also asked some of the larger corporations in the region to sponsor the festival. Because the festival was so ambitious and so exciting, many, many businesses gave of their time, money, and products.

List

Some of our sponsors and donors included:

Listings Beverages

Meagan’s Bakery

SonicLand Sound and Lights

Mifflin Stage Technology

Dommy’s Restaurant

Callahan’s Tire and Auto

Riverside Hotel

East Park Motor Inn

Jim and Mike’s Party Supply

Paper Clip Supply Co.

Glan-Allin Music Shops

Clanders River Valley Magazine

Guinea Hen Café

Langley’s Pizza

The Daily Tribune

Mondale Hotel

Vendors

Introduction

We decided to have the vendors XE "vendors"  congregated along the west side of the park. Initially we were just going to have food and beverage vendors, but then we decided to include crafts, clothing, and CD sellers (just for the participating musicians XE "musicians"  and for some of the smaller record labels producing those musicians). 

Selection Process

We put ads in local publications and some of the smaller music XE "music"  magazines. We put a deadline for bids. We sought vendors XE "vendors"  that could contribute to the diverse cultural nature of the festival XE "festival" . We also asked potential vendors to describe their experience selling at festivals. As the bids came in, we sorted them into different categories. We also sorted them into yes/no/maybe columns. We ended up selecting vendors based on a number of factors including variety and affordability. For example, for food vendors, we wanted a mix of international foods, vegetarian options, and some (but not many) of the usual sorts of festival foods. 

Recommendations

Clustering the vendors XE "vendors"  by type, i.e., food, crafts, CD sales, etc., would probably help with foot-traffic flow. While it probably did not hurt sales, the food lines were very long and interfered with lines for the other, non-food vendors. Also, it would be a good idea to draft rules about set-up and take-down times.

In addition, we could probably just have vendors XE "vendors"  of international foods. This will not only contribute to the festival XE "festival"  experience but also, quite frankly, the hot dog and funnel cake vendors reported poor sales, while the other vendors reported heavy sales. Clearly C.I.O.M.F. XE "C.I.O.M.F." \t "See festival"  attendees seek a fully diverse cultural experience, which is something to keep in mind when soliciting vendors for future festivals. 

Children’s Area

Introduction

We had 12 volunteer child care providers, many of them certified. The children’s area was on the north side of the park near the playground. Younger children had a fenced-off area to provide a safe place to play. Nearby, we had tables for face painting, balloon animals, pottery painting, finger painting, and instrument making.

Recommendations

We think that the pottery painting was perhaps a little too messy and high-maintenance to be a good activity for next year’s festival XE "festival" . The instrument making was very, very popular, but we recommend that next year’s organizers start collecting donated materials earlier than we did! Parents and friends were more than happy to provide needed items, but we ran out of cardboard tubes on the second day and rubber bands that same afternoon. 

Conclusion

We would like to see the festival XE "festival"  continue as an annual event. Our strongest recommendations include:

1. Plan early.

2. Plan thoroughly.

3. Make backup plans—for example, if a musician’s flight gets cancelled or a thunderstorm rolls in.

4. Be flexible (see number 3).

5. Remember, the festival XE "festival"  is supposed to be fun for everyone, including the organizers.

6. Do not be afraid to ask for help—from the community, from vendors XE "vendors" , from sponsors and donors.

Index



bands. See musicians

C.I.O.M.F.. See festival

festival, 2, 4, 5, 6, 7, 8

music, 2, 4, 6

musicians, 2, 4, 6

vendors, 2, 4, 6, 8



