Strengthening Routine Immunization in Dakshin Dinajpur

	Demographic
	2001 Census

	Population
	1502647

	Sex  Ratio
	950

	Urban population
	12. 6%


	Administrative
	

	Subdivisions
	2

	Panchayat samitis
	8

	Gram Panchayats
	64

	Municipality
	2


	Health Infrastructure
	

	Hospitals
	3

	BPHC
	8

	PHC
	20

	Health Sub Centres
	247


	RCH INDICATORS- DAKSHIN DINAJPUR (Rapid Household Survey 1999)
	State

	Girls married <18 Years
	51.1

	Third & higher order birth reported
	38.5

	C.B.R. Per thousand
	21.2

	Pregnant women who had T.T. twice.
	86.4*

	Children immunized (DPT-3, Polio-3, BCG, Measles)
	51.5*


State

District

 IMR

52

61

MMR
2.64

2.5

NMR

35

42

	RCH II OBJECTIVES
	D  I  S  T  R  I  C  T

	
	Present Position
	Short Term By 2007
	Long Term By 2010

	MMR
	250
	200
	150

	IMR
	61
	50
	35

	NMR
	42
	35
	20

	INSTITUTIONAL

DELIVERY
	30%
	50%
	80%

	CPR
	50%
	60%
	70%

	COMPLETE 

IMMUNIZATION
	62%
	75%
	100%

	ANC 3 CHECK UPS
	55%
	-
	100%

	POST NATAL 3 CHECK UPS
	49%


	70%
	90%


UNICEF interventions in the district

UNICEF started systematic interventions in the district to strengthen routine immunization in June 2004. A number of activities were initiated and key technical, logistic and financial inputs were provided which resulted in regular outreach sessions at sub centre level and improved quality of cold chain and sterilization, regular and improved monitoring, enhanced participation of local government institutions (Gram Panchayat)

UNICEF planned the following interventions:

· Framework for microplan

· Developing instrument for monitoring of subcentres and immunization sessions

· Supply of cold chain equipment

· Mobility of health workers for outreach sessions in 2004

· AD syringes

· Community Involvement / ownership of the PRI – GP level meeting, 

· Tagging of SHGs with sub centers

· Analysing the present status- performance by sub centre and putting the data in GIS

· Technical, social mobilization, advocacy, monitoring support

· Funds-Rs 35000 directly to the district for training in February and March 2005

· Setting up of Routine immunization and Polio Eradication cell at office of CMOH with one Social Mobilization Officer and one Data Entry Operator. The Cell is functioning since February 2005 and was involved in computerizing micro planning data as well as monitoring sub center activities. Now it monitors CBDP work.

· Extended critical support to SIA since April 2005 through integrated advocacy and strategic planning with general administration, Panchayats, health functionaries, ICDS and NGOs

· Deployment of Social Mobilizers through NGOs (Social Welfare Institute) and District Madrassah Board

· Urban outreach immunization

· Nutrition interventions (Positive Deviance) through Shibpur People’s Cooperative (SPCO), Tapan

· Total Sanitation through Tagore Society for Rural Development, Balapur

· Regular monitoring at Malahar village and setting up a new sub center

· Involvement in RCH II District Plan Process

.
	Immunization in 2006-07 compared to last 7 years Dakshin Dinajpur

	Antigen
	1999
	2000
	2001
	2002
	2003
	2004 -05
	2005-06
	2006-07

	TT (PW)
	21645
	25373
	24350
	26401
	26246
	27649+ 3380 Pvt
	29346 + Pvt
	30070+ Pvt

	BCG
	27066
	29834
	31701
	30570
	32852
	33588
	34032
	34474

	OPV
	26423
	27983
	27298
	27396
	29941
	30425
	32932
	31103

	DPT
	26238
	28227
	27191
	27360
	30360
	30431
	33016
	31090

	Measles
	22432
	23185
	26986
	25416
	22274
	29547
	30644
	30430

	Vita A
	23504
	23718
	26684
	25356
	23186
	29802
	30857
	32524


	 
	TT (PW)
	BCG
	OPV

	Name of Centre
	ELA 2006-07
	Performance
upto March 2007
	Performance upto Mar- 2006
	Performance upto March 2005
	Percent increased or decreased 
in comparison with last yrs' performance
	ELA 2006-07
	Performance
upto March 2007
	Performance upto Mar- 2006
	Performance upto March 2005
	Percent increased or decreased 
in comparison with last yrs' performance
	Performance
upto March2007
	Performance upto Mar- 2006
	Performance upto March 2005
	Percent increased or decreased 
in comparison with last yrs' performance

	PP Unit Balurghat
	2525
	1703
	1331
	1766
	25.68
	2243
	3888
	3000
	2479
	29.60
	2147
	1990
	1744
	7.89

	PP Unit Gangarampur
	1316
	600
	417
	389
	43.54
	1184
	1882
	1039
	1025
	81.14
	558
	422
	435
	32.23

	Khaspur BPHC
	5498
	4287
	4014
	3798
	4.56
	4948
	4375
	4638
	4708
	-5.67
	4450
	4593
	4937
	-3.11

	Hili Rural Hospital
	2008
	1890
	1465
	1410
	21.31
	1826
	1771
	1822
	1697
	-2.80
	1740
	1915
	1552
	-9.14

	Kumarganj BPHC
	3653
	3114
	3125
	3094
	-0.51
	3288
	3304
	3362
	3411
	-1.73
	3167
	3543
	3230
	-10.61

	Tapan BPHC
	6442
	4408
	4342
	4335
	0.62
	5798
	4639
	4898
	5248
	-5.29
	4512
	5147
	4642
	-12.34

	Gangarampur BPHC
	5808
	4534
	4993
	4528
	-9.97
	5227
	4900
	5350
	5325
	-8.41
	4704
	5384
	4973
	-12.63

	Banshihari BPHC
	3123
	2532
	2352
	2310
	2.68
	2811
	2646
	2634
	2884
	0.46
	2651
	2868
	2514
	-7.57

	Harirampur BPHC
	3753
	2981
	2625
	2313
	2.76
	3378
	3236
	3195
	2678
	1.28
	3200
	2983
	2461
	7.27

	Kushmandi BPHC
	4901
	4021
	3710
	3706
	0.50
	4422
	3833
	4094
	4133
	-6.38
	3974
	4087
	3937
	-2.76

	DISTRICT TOTAL
	39027
	30070
	28374
	27649
	2.47
	35125
	34474
	34032
	33588
	1.30
	31103
	32932
	30425
	-5.55


	 
	DPT
	MEASLES
	VITA A

	Name of Centre
	ELA 2006-07
	Performance
upto March2007
	Performance up to Mar- 2006
	Performance upto March 2005
	Percent increased or decreased 
in comparison with last yrs' performance
	Performance
upto March 2007
	Performance upto Mar- 2006
	Performance upto March 2005
	Percent increased or decreased 
in comparison with last yrs' performance
	Performance
upto March 2007
	Performance upto Mar- 2006
	Performance upto March 2005
	Percent increased or decreased 
in comparison with last yrs' performance

	1. PP Unit Balurghat
	2243
	2153
	1990
	1791
	8.19
	1808
	1910
	1339
	-5.34
	1826
	1677
	1363
	8.88

	2. PPU Gangarampur
	1184
	558
	422
	435
	32.23
	588
	378
	458
	55.56
	588
	379
	506
	55.15

	3. Khaspur BPHC
	4948
	4435
	4707
	4910
	-5.78
	4356
	4507
	4764
	-3.35
	6183
	4360
	4848
	41.81

	4. Hili Rural Hospital
	1826
	1740
	1915
	1548
	-9.14
	1749
	1751
	1466
	-0.11
	1749
	1769
	1542
	-1.13

	5. Kumarganj BPHC
	3288
	3167
	3575
	3263
	-11.41
	3132
	3464
	3290
	-9.58
	3132
	3467
	3050
	-9.66

	6 Tapan BPHC
	5798
	4512
	5149
	4711
	-12.37
	4580
	4852
	5080
	-5.61
	4580
	4905
	5080
	-6.63

	7 Gangarampur BPHC
	5227
	4704
	5384
	4663
	-12.63
	4709
	4951
	4598
	-4.89
	4714
	5012
	4477
	-5.95

	8.Banshihari BPHC
	2811
	2649
	2795
	2585
	-5.22
	2462
	2324
	2200
	5.94
	2570
	2681
	2617
	-4.14

	9. Harirampur BPHC
	3378
	3206
	2993
	2536
	7.12
	3214
	2846
	2306
	12.93
	3339
	2930
	2203
	13.96

	10.Kushmandi BPHC
	4422
	3966
	4086
	3989
	-2.94
	3832
	3661
	4046
	4.67
	3843
	3677
	4116
	4.51

	DISTRICT TOTAL
	35125
	31090
	33016
	30431
	-5.83
	30430
	30644
	29547
	-0.70
	32524
	30857
	29802
	5.40


Maps showing performance up to March 2007 

[image: image1.bmp]
Measles

[image: image2.bmp][image: image3.bmp][image: image4.bmp]




The concerns remaining

· Drop in BCG coverage in most blocks and drop in DPT, OPV and Measles in district as a whole

· Closed sub centers when HA F go for training

· Quality of immunization- shortages and uneven practice in sterilization

· Disposal of used syringes and needles

· MIS- Inaccurate ELA used for year 2006-07

 
































































Hilli





Balurghat





Kumarganj





Gangarampur





Kushmundi





Bansihari








Drop in coverage





Static coverage





>5% increase





>10% increase





Percent



































Tapan





Harirampur








_1188189428.xls
FW-1

		Review of  Family Welfare, RCH & Immunisation  Programmes in Dakshin Dinajpur District From April-2005 To July-2005.

				VASECTOMY										TUBECTOMY										TOTAL STERILISATION(M+F)

		Name of Centre		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance

		1. PP Unit Balurghat		6		0		0.00		0		0		850		78		9.18		57		36.84		856		78		9.11		57		36.84

		2. PP Unit Gangarampur		3		0		0.00		0		0		290		34		11.72		187		-81.82		293		34		11.60		187		-81.82

		3. Khaspur BPHC		15		9		60.00		0		0		1300		0		0.00		814		-100.00		1315		9		0.68		814		-98.89

		4. Hili Rural Hospital		11		0		0.00		0		0		500		95		19.00		43		0.00		511		95		18.59		43		120.93

		5. Kumarganj BPHC		12		0		0.00		0		0		1000		109		10.90		537		-79.70		1012		109		10.77		537		-79.70

		6 Tapan BPHC		13		0		0.00		0		0		900		34		3.78		0		0.00		913		34		3.72		0		0.00

		7 Gangarampur BPHC		10		0		0.00		0		0		1500		0		0.00		959		-100.00		1510		0		0.00		959		-100.00

		8.Banshihari BPHC		6		0		0.00		0		0		400		0		0.00		0		0.00		406		0		0.00		0		0.00

		9. Harirampur BPHC		8		0		0.00		0		0		1300		0		0.00		938		-100.00		1308		0		0.00		938		-100.00

		10.Kushmandi BPHC		8		0		0.00		0		0		900		0		0.00		463		-100.00		908		0		0.00		463		-100.00

		DISTRICT TOTAL		92		9		9.78		0		0		8940		350		3.91		3998		-91.25		9032		359		3.97		3998		-91.02





FW-2

		

				IUD INSERTIONS										OP CYCLES										CC IN PCS

		Name of Centre		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance

		1. PP Unit Balurghat		160		7		4.38		28		-75.00		4329		2511		58.00		1116		125.00		43992		18275		41.54		2709		574.60

		2. PP Unit Gangarampur		52		4		7.69		9		-55.56		2665		269		10.09		272		-1.10		9000		11000		122.22		580		1796.55

		3. Khaspur BPHC		100		34		34.00		9		0		16796		3769		22.44		3561		5.84		108792		21528		19.79		35769		-39.81

		4. Hili Rural Hospital		50		38		76.00		1		0		5356		1943		36.28		1659		17.12		18792		7747		41.22		4464		73.54

		5. Kumarganj BPHC		180		47		26.11		19		0		15301		3421		22.36		3047		12.27		63936		17399		27.21		14903		16.75

		6 Tapan BPHC		125		110		88.00		3		0		19292		3864		20.03		3838		0.68		94896		15731		16.58		11594		35.68

		7 Gangarampur BPHC		75		11		14.67		5		120.00		13156		3384		25.72		2945		14.91		53712		16851		31.37		11017		52.95

		8.Banshihari BPHC		150		42		0.00		16		0		8060		1730		21.46		2269		-23.75		67680		7066		10.44		12845		-44.99

		9. Harirampur BPHC		100		57		57.00		0		0		5265		1743		33.11		1639		6.35		71640		23269		32.48		10267		126.64

		10.Kushmandi BPHC		75		46		61.33		9		411.11		9178		2274		24.78		2100		8.29		50760		25865		50.96		10099		156.11

		DISTRICT TOTAL		1067		396		37.11		99		300.00		99398		24908		25.06		22446		10.97		583200		164731		28.25		114247		44.19

																				0.00





IMMU-1

		STATUS OF IMMUNISATION IN DAKSHIN DINAJPUR DISTRICT UPTO DECEMBER-2004.

				BCG								OPV								DPT								MEASLES								VITA. A								TT(PW)

		Name of Centre		ELA-2004-2005		Performance upto March-2005		Percent achieved upto March-2005		INDICATOR		ELA-2004-2005		Performance upto March-2005		Percent achieved upto March-2005		INDICATOR		ELA-2004-2005		Performance upto March-2005		Percent achieved upto March-2005		INDICATOR		ELA-2004-2005		Performance upto March-2005		Percent achieved upto March-2005		INDICATOR		ELA-2004-2005		Performance upto March-2005		Percent achieved upto March-2005		INDICATOR		ELA-2004-2005		Performance upto March-2005		Percent achieved upto March-2005		INDICATOR

		1. PP Unit Balurghat		2989				0				2989				0.00				2989				0				2989				0.00				2989				0.00				3321				0.00

		2. PP Unit Gangarampur		1100				0				1100				0.00				1100				0				1100				0.00				1100				0.00				1223				0.00

		3. Khaspur BPHC		5015				0				5015				0.00				5015				0				5015				0.00				5015				0.00				5572				0.00

		4. Hili Rural Hospital		1704				0				1704				0.00				1704				0				1704				0.00				1704				0.00				1893				0.00

		5. Kumarganj BPHC		2782				0				2782				0.00				2782				0				2782				0.00				2782				0.00				3091				0.00

		6 Tapan BPHC		4985				0				4985				0.00				4985				0				4985				0.00				4985				0.00				5539				0.00

		7 Gangarampur BPHC		4382				0				4382				0.00				4382				0				4382				0.00				4382				0.00				4869				0.00

		8.Banshihari BPHC		2467				0.00				2467				0.00				2467				0				2467				0.00				2467				0.00				2741				0.00

		9. Harirampur BPHC		2728				0				2728				0.00				2728				0				2728				0.00				2728				0.00				3031				0.00

		10.Kushmandi BPHC		3791				0				3791				0.00				3791				0				3791				0.00				3791				0.00				4212				0.00

		DISTRICT TOTAL		31943				0				31943				0.00				31943				0				31943				0.00				31943				0.00				35492				0.00





chart 1

		





chart 1

		2989

		1100

		5015

		1704

		2782

		4985

		4382

		2467

		2728

		3791



ELA-2004-05

Performance

UNIT WISE STATUS OF BCG



chart 2

				DPT				OPV				DPT				MEASLES

				Target-2003-04		Achievement		Target-2003-04		Achievement		Target-2003-04		Achievement		Target-2003-04		Achievement

		1. PP Unit Balurghat		2478		1984		2350		1984		2350		2041		2350		1211

		2. PP Unit Gangarampur		1051		358		995		358		995		365		995		285

		3. Khaspur BPHC		4540		4711		5270		4711		5270		4755		5270		3571

		4. Hili Rural Hospital		1654		1517		1868		1517		1868		1545		1868		1214

		5. Kumarganj BPHC		3452		3385		3585		3385		3585		3455		3585		2578

		6 Tapan BPHC		5084		4380		5237		4380		5237		4435		5237		3589

		7 Gangarampur BPHC		5099		4781		4797		4781		4797		4818		4797		2951

		8.Banshihari BPHC		2903		2471		2883		2471		2883		2553		2883		1669

		9. Harirampur BPHC		2517		2242		2947		2242		2947		2300		2947		1855

		10.Kushmandi BPHC		4074		4112		4080		4112		4080		4093		4080		3351





chart 2

		2989

		1100

		5015

		1704

		2782

		4985

		4382

		2467

		2728

		3791



ELA-2004-05

PERFORMANCE

UNIT WISE STATUS OF OPV



IMMU-4

		





IMMU-4

		2989

		1100

		5015

		1704

		2782

		4985

		4382

		2467

		2728

		3791



ELA-2004-05

PERFORMANCE

UNIT WISE STATUS OF DPT



IMMU-5

		





IMMU-5

		2989

		1100

		5015

		1704

		2782

		4985

		4382

		2467

		2728

		3791



ELA-2004-05

PERFORMANCE

UNIT WISE STATUS OF MEASLES



IMMU-6

		





IMMU-7

		1. PP Unit Balurghat		1430		1984

		2. PP Unit Gangarampur		239		358

		3. Khaspur BPHC		4018		4711

		4. Hili Rural Hospital		1580		1517

		5. Kumarganj BPHC		3192		3385

		6 Tapan BPHC		4849		4380

		7 Gangarampur BPHC		4419		4781

		8.Banshihari BPHC		872		2471

		9. Harirampur BPHC		3097		2242

		10.Kushmandi BPHC		3700		4112





IMMU-7

		

		0

		Name of Centre		Name of Centre

		PP Unit Balurghat		PP Unit Balurghat

		PP Unit Gangarampur		PP Unit Gangarampur

		Khaspur BPHC		Khaspur BPHC

		Hili Rural Hospital		Hili Rural Hospital

		Kumarganj BPHC		Kumarganj BPHC



Pwerformance for 2002-03

Performance for 2003-04

Performance of OPV in 2002-2003 & 2003-2004

0

0

3548

48

1309

24

5953

146

2023

66

3427

164



RCH

		REVIEW OF REPRODUCTIVE & CHILD HEALH PROGRAMME IN DAKSHIN DINAJPUR DURING FROM APRIL- 2005 TO JULY-2005

				ANC REGISTERED						ANC 3 CHECK UP						High Risk Pregnancies						TOTAL NO.OF DELIVERIES UPTO July-2005

		Name of Centre		ELA 2005-
2006		ANC regd.
 Upto July-05		Percent
achieved		ELA 2004-
2005		3 Ch.up
 Upto July-05		Percent
achieved		ELA 2004-
2005		No. of high
risk preg-
nancies reported
upto July-
2005		Percent		ELA 2004-
2005		Deliveries
by trained
attendant		Deliveries by UTBA		Institutional		Total		Percent
of total
delivery

		PP Unit Balurghat		3548		486		13.70		3548		285		8.03		532		0		0.00		3225		0		0		1491		1491		46.23

		PP Unit Gangarampur		1309		297		22.69		1309		107		8.17		196		0		0.00		1190		0		0		0		0		0.00

		Khaspur BPHC		5953		1186		19.92		5953		888		14.92		893		60		6.72		5390		387		87		46		520		9.65

		Hili Rural Hospital		2023		368		18.19		2023		204		10.08		303		30		9.90		1839		80		23		110		213		11.58

		Kumarganj BPHC		3427		1007		29.38		3427		656		19.14		514		26		5.06		3115		350		32		177		559		17.95

		Tapan BPHC		5918		1229		20.77		5918		1049		17.73		888		30		3.38		5380		955		30		348		1333		24.78

		Gangarampur SD Hos.		5202		1223		23.51		5202		733		14.09		780		13		1.67		4729		646		45		590		1281		27.09

		Banshihari BPHC		2929		777		26.53		2929		350		11.95		439		51		11.62		2663		292		120		86		498		18.70

		Harirampur BPHC		3238		769		23.75		3238		982		30.33		486		25		5.14		2944		382		72		124		578		19.63

		Kushmandi BPHC		4500		1480		32.89		4500		792		17.60		675		65		9.63		4091		794		22		157		973		23.78

		DISTRICT TOTAL		38047		8822		23.19		38047		6046		15.89		5706		300		5.26		34566		3886		431		3129		7446		21.54

						Total		Deliveries
by trained
attendant		Deliveries
by un-trained
attendant		Institutional

		Khaspur BPHC		6.03		1790		1302		380		108

		Hili Rural Hospital		57.66		862		329		36		497

		Kumarganj BPHC		32.79		1668		1009		112		547

		Tapan BPHC		22.87		3577		2281		478		818

		Gangarampur SD Hos.		38.32		4061		2333		172		1556

		Banshihari BPHC		6.54		1775		1218		441		116

		Harirampur BPHC		20.61		1980		1274		298		408

		Kushmandi BPHC		10.92		3645		3137		110		398





Chart1

		PP Unit Balurghat		PP Unit Balurghat		PP Unit Balurghat

		PP Unit Gangarampur		PP Unit Gangarampur		PP Unit Gangarampur

		Khaspur BPHC		Khaspur BPHC		Khaspur BPHC

		Hili Rural Hospital		Hili Rural Hospital		Hili Rural Hospital

		Kumarganj BPHC		Kumarganj BPHC		Kumarganj BPHC

		Tapan BPHC		Tapan BPHC		Tapan BPHC

		Gangarampur SD Hos.		Gangarampur SD Hos.		Gangarampur SD Hos.

		Banshihari BPHC		Banshihari BPHC		Banshihari BPHC

		Harirampur BPHC		Harirampur BPHC		Harirampur BPHC

		Kushmandi BPHC		Kushmandi BPHC		Kushmandi BPHC

		Private Nursing Homes		Private Nursing Homes		Private Nursing Homes

		DISTRICT TOTAL		DISTRICT TOTAL		DISTRICT TOTAL



TT

BCG

OPV 3

Percent achieved upto July -2005

Percent achieved upto July -2005

Percent achieved upto July -2005

10.6820744081

27.3178294574

14.5426356589

15.2788388083

25.7983193277

16.3025210084

19.9059297833

20.4692407168

26.3994088306

20.3657933762

20.1740076128

24.5785753127

25.8535161949

31.3643659711

34.0288924559

17.9959445759

24.9814126394

28.9776951673

22.7220299885

27.8705857475

35.3140198774

23.830658928

19.8272624859

27.9384153211

23.131562693

24.7282608696

22.4184782609

29.7777777778

25.7394280127

27.9393791249

21.2789444634

24.9067622655

27.1184480615



Comparison-1

		

																		Page-3-

				TT (PW)										IFA to ANCs										BCG										OPV

		Name of Centre		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance

		PP Unit Balurghat		3548		379		10.68		362		4.70		3548		488		13.75		356		37.08		3225		881		27.32		670		31.49		3225		469		14.54		482		-2.70

		PP Unit Gangarampur		1309		200		15.28		107		86.92		1310		563		42.98		294		91.50		1190		307		25.80		244		25.82		1190		194		16.30		180		7.78

		Khaspur BPHC		5953		1185		19.91		723		63.90		5954		1903		31.96		920		106.85		5413		1108		20.47		1308		-15.29		5413		1429		26.40		1271		12.43

		Hili Rural Hospital		2023		412		20.37		401		2.74		2024		916		45.26		404		126.73		1839		371		20.17		455		-18.46		1839		452		24.58		468		-3.42

		Kumarganj BPHC		3427		886		25.85		497		78.27		3428		1323		38.59		524		152.48		3115		977		31.36		930		5.05		3115		1060		34.03		833		27.25

		Tapan BPHC		5918		1065		18.00		1018		4.62		5918		1669		28.20		276		504.71		5380		1344		24.98		1317		2.05		5380		1559		28.98		1308		19.19

		Gangarampur SD Hos.		5202		1182		22.72		942		25.48		5202		1393		26.78		297		369.02		4729		1318		27.87		1348		-2.23		4729		1670		35.31		1197		39.52

		Banshihari BPHC		2929		698		23.83		557		25.31		2930		1362		46.48		431		216.01		2663		528		19.83		736		-28.26		2663		744		27.94		682		9.09

		Harirampur BPHC		3238		749		23.13		470		59.36		3238		1792		55.34		246		628.46		2944		728		24.73		780		-6.67		2944		660		22.42		651		1.38

		Kushmandi BPHC		4500		1340		29.78		994		34.81		4500		4334		96.31		608		612.83		4091		1053		25.74		1239		-15.01		4091		1143		27.94		1006		13.62

		Private Nursing Homes

		DISTRICT TOTAL		38047		8096		21.28		6071		33.36		38052		15743		41.37		4356		261.41		34589		8615		24.91		9027		-4.56		34589		9380		27.12		8078		16.12





Chart2

		1. PP Unit Balurghat		1. PP Unit Balurghat

		2. PP Unit Gangarampur		2. PP Unit Gangarampur

		3. Khaspur BPHC		3. Khaspur BPHC

		4. Hili Rural Hospital		4. Hili Rural Hospital

		5. Kumarganj BPHC		5. Kumarganj BPHC

		6 Tapan BPHC		6 Tapan BPHC

		7 Gangarampur BPHC		7 Gangarampur BPHC

		8.Banshihari BPHC		8.Banshihari BPHC

		9. Harirampur BPHC		9. Harirampur BPHC

		10.Kushmandi BPHC		10.Kushmandi BPHC

		DISTRICT TOTAL		DISTRICT TOTAL



DPT

Measles

Percent achieved upto July -2005

Percent achieved upto July -2005

14.5426356589

13.2713178295

16.3025210084

10

26.2885645668

20.3029743211

24.4698205546

20.3371397499

34.3499197432

26.3563402889

29.0148698885

23.9591078067

35.5254810742

25.0158595898

28.163725122

19.7146075854

22.4184782609

19.191576087

28.0371547299

23.0505988756

27.1878342826

21.2379658273



Comparison-2

		

				DPT										MEASLES										VITA A										DT

		Name of Centre		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance		ELA-2005-2006		Performance upto July- 2005		Percent achieved upto July -2005		Performance upto July- 2004		Percent increased or decreased 
in comparison with last yrs' performance

		1. PP Unit Balurghat		3225		469		14.54		499		-6.01		3225		428		13.27		356		20.22		3225		417		12.93		357		16.81		3002		350		11.66		314		11.46

		2. PP Unit Gangarampur		1190		194		16.30		180		7.78		1190		119		10.00		156		-23.72		1190		122		10.25		185		-34.05		1108		95		8.57		66		43.94

		3. Khaspur BPHC		5413		1423		26.29		1213		17.31		5413		1099		20.30		1491		-26.29		5413		1117		20.64		1490		-25.03		5037		985		19.56		655		50.38

		4. Hili Rural Hospital		1839		450		24.47		462		-2.60		1839		374		20.34		470		-20.43		1839		388		21.10		516		-24.81		1513		377		24.92		17		2117.65

		5. Kumarganj BPHC		3115		1070		34.35		836		27.99		3115		821		26.36		799		2.75		3115		822		26.39		756		8.73		2900		832		28.69		292		184.93

		6 Tapan BPHC		5380		1561		29.01		1308		19.34		5380		1289		23.96		1192		8.14		5380		1314		24.42		885		48.47		5009		1493		29.81		326		357.98

		7 Gangarampur BPHC		4729		1680		35.53		1128		48.94		4729		1183		25.02		1084		9.13		4729		1217		25.73		757		60.77		4403		864		19.62		186		364.52

		8.Banshihari BPHC		2663		750		28.16		711		5.49		2663		525		19.71		619		-15.19		2663		568		21.33		780		-27.18		2479		470		18.96		257		82.88

		9. Harirampur BPHC		2944		660		22.42		695		-5.04		2944		565		19.19		623		-9.31		2944		602		20.45		522		15.33		2741		374		13.64		499		-25.05

		10.Kushmandi BPHC		4091		1147		28.04		1060		8.21		4091		943		23.05		1035		-8.89		4091		958		23.42		860		11.40		3808		874		22.95		226		286.73

		DISTRICT TOTAL		34589		9404		27.19		8092		16.21		34589		7346		21.24		7825		-6.12		34589		7525		21.76		7108		5.87		32000		6714		20.98		2838		136.58





Comparison-3

		

		IMMUNISATION EFFCIENCY : BLOCK LEVEL COMPARISON : DAKSHIN DINAJPUR: RCH-2002-03.

		Block/Urban		TT(PW)		BCG		DPT		POLIO		MEASLES		VITA. A

		PP Unit Balurghat		43.74		103.27		61.95		65.00		49.50		46.50

		PP Unit Gangarampur		35.16		60.04		26.53		26.53		22.97		25.19

		Khaspur BPHC		66.92		85.09		76.67		74.05		74.07		76.02

		Hili Rural Hospital		82.78		93.08		97.38		94.22		90.58		92.84

		Kumarganj BPHC		77.65		101.81		98.28		98.03		90.14		88.14

		Tapan BPHC		80.63		87.97		96.21		94.25		91.29		82.92

		Gangarampur SD Hos.		89.02		108.00		98.42		98.22		81.08		82.15

		Banshihari BPHC

		Harirampur BPHC		72.56		93.48		72.05		75.52		70.51		74.17

		Kushmandi BPHC		80.53		106.53		96.7		99.38		96.59		99.22

		Dakshin Dinajpur		74.29		95.28		85.28		85.39		79.22		79.03

		IMMUNISATION EFFCIENCY : BLOCK LEVEL COMPARISON : DAKSHIN DINAJPUR: RCH-2003-04.

		Block/Urban		TT(PW)		BCG		DPT		POLIO		MEASLES		VITA. A

		PP Unit Balurghat		42.40		105.45		86.85		84.43		49.53		48.95

		PP Unit Gangarampur		36.38		105.63		36.68		35.98		28.64		29.30

		Khaspur BPHC		62.21		86.16		90.23		89.39		67.76		78.26

		Hili Rural Hospital		64.00		88.54		82.71		81.21		64.99		91.15

		Kumarganj BPHC		70.22		96.29		96.37		94.42		71.91		87.12

		Tapan BPHC		77.44		96.08		84.69		83.64		68.53		84.25

		Gangarampur SD Hos.		78.07		106.30		100.40		99.67		61.52		83.34

		Banshihari BPHC		69.00		100.69		88.55		85.71		60.89		81.24

		Harirampur BPHC		67.50		85.41		78.05		76.08		62.95		75.31

		Kushmandi BPHC		85.62		99.85		100.30		100.80		82.13		97.26

		Dakshin Dinajpur		69.45		96.59		89.26		88.03		65.49		70.23

		Legend:

				Below 70%		Below 70%		Below 60%		Below 60%		Below50%		Below50%

				70-80%		60-75%		60-75%		50-70%		60-80%		50-70%

				Above 85%		Above 85%		Above75%		Above75%		Above80%		Above70%






