CRUMBS Tech Schedule

Load-in, Tech Week, Strike, and More!

Last Updated 5/24, 9 AM

KSC= Kennedy Space Center, KT = Kennedy Theatre

Please review each item on the schedule for accuracy and let me know of any errors or confusing sections.

Please contact Andy Hayworth with questions.  Contacting Dennis Johnson on load-in questions is a good idea.

SATURDAY MAY 24

No rehearsal

Work in morning?

5:00 PM
Paper tech with SMgt and Carmen - KSC

7:00 PM
Paper tech with Carmen, Andy, Chris B., Jeremy - KSC

7:00 PM - ?
Rehearsal space - Strike set, load onto trailer, take it to the Kennedy Theatre (We 

will be leaving it on the trailer).  ASMs pack-up and load props into Andy’s van.

SUNDAY, MAY 25

8:00 AM
Kennedy Theatre - Stage Management Crew (Andy, NoL, Amber, Kim) will tape 

out set on floor.

Chris and a small crew (2 people) will hang and focus lights.

Crew (Dennis, Jerry, Chris H., Zack, Adam, Chris V., Jenni) will move platforms 

into theatre (around the perimeter.)

9:30 AM
Radio Interview - Shaw Univ. - Simmie, Hope, Rowena

2:00 - 5:00
Cast Rehearse at KSC.

Work and clean up complete in time for run at 7:30 PM.

6:00 - 11:00
Cast rehearse at Kennedy Theatre. (6:00 Call, 7:30 Go)

MONDAY, MAY 26

    Crew is off this day (Holiday) - we can’t get into KT.

6:30 PM
ASM/Dresser call

7:00 PM
Cast rehearse in evening at Rehearsal Space.  Hair and makeup.

TUESDAY MAY 27

8:00 AM - 6:00 PM - Work on sets and lights, touchups (Light crew, Set crew)

6:00 PM - 11:00 PM - Rehearsal

6:00 PM
Cast call

6:30 PM
Go

Archival photos - afterward?  during?

WEDNESDAY MAY 28

8:00 AM - 6:00 PM - Finish sets and lights as needed.

6:00 PM - 11:00 PM - Dress Rehearsal - some audience

7:30 PM
Go

THURSDAY, MAY 29

6:00 PM
Crew Call ?

7:00 PM
Cast Call

June 10 - scene at St. Augustine’s in evening

June 14 - Fundraising Performance and Talkback Session

Dennis Johnson, TD




Andy Hayworth, PSM

910-890-3437





919.557.9781 (home) or 910.890.4272 (cell)

dennis@jbrothers.net




thehayworth@yahoo.com
