Oxford Brookes University

Department of Computing

U08784 – Software Project Management

Week 1 Exercises

________________________________________________________________________________









Construct a Network Diagram
Steps in Constructing a Network Diagram


Step

1 
Prepare a work breakdown structure

2
Estimate the duration of activities

3
Establish logical sequence between activities (dependencies)

4
Draw the basic network in rough

5
Calculate the total project time and floats

6
Identify activities on the critical path

7
Allocate resources

8
Smooth out the network

9
Check the network

10 
Discuss and refine until it is appropriate

Scenario



You are project manager for a project that involves developing the software for a small cash and carry organisation.  The design is complete and you are responsible for coding and implementing the system.  
STEPS 1-3  HAVE BEEN COMPLETED AS BELOW. 






ACTIVITY
DURATION
DEPENDS



(Weeks)
ON

10
Confirm Design

2

15
Prepare Room

6

20
Install Network

9
15

25
Test Hardware

2
20

30
Write data entry software

3
10

40
Create Data files

5
30

50
Do Stock update

3
40

60
Write Program Specs.

3
10

70
Construct Programs

12
60

80
Test System

5
25, 70, 40

90
Familiarise users

2
10

100Train Staff

6
90 

110Handover

2
100, 80, 50

From this table it is now possible to draw a network and calculate the total project time and the critical path for this project 
STEP 4

DRAW THE BASIC NETWORK 



Draw the basic logic diagram from the activity list in the scenario.

Hints

*
It will be impossible to get your chart right first time so draw in pencil on a large sheet of paper. 

*
Draw the first event node which represents “Start of Project"

*
Draw those activities which can be started right away because they are not dependent on any event except the start of the project, as lines emanating from the first event,

*
Remember that each activity is terminated by an event (or node) 

*
Work from left to right drawing logic of the network


Activity descriptions or codes are written above the arrows representing them. The duration of the activity is written below the arrow.

*
The network should be simple and attractive to use

*
Activity lines should be drawn so that they do not cross, but dummy activities may cross activity arrows.

STEP 5

Calculate the total project time and float 
 
Update the network to show the earliest time by which event could be completed and then from that calculate the earliest time by which the project could be completed.

*
Start on the left of the network at the first event; give this event an EST of 0. This does not mean that all emerging events must start right away just that they are not dependent on any previous event

*
Work from left to right and calculate and enter the earliest time at which each event can occur by adding the duration times to the preceding EST. When several activities lead into an event, the earliest time for the completion of that event is fixed by the chain which has the longest total duration. The correct choice for the earliest time is the largest figure of the alternatives.

*
The total project time is the earliest time for the final event.
STEP 6


Identify the critical path  
Show the critical path on your diagram

*
Start from the right of the network at the last event and give this event a LST equal to its EST

*
Proceed in order and calculate and enter the LST at which each event can occur by subtracting the duration times. When several activities lead into an event, the LST is fixed by the chain which has longest total duration.  The correct choice for the LST is the smallest of alternative figures.

*
The critical path lies along those lies along those activities which satisfy all these rules:


a)
Earliest and latest times for tail events are the same.


b)
Earliest and latest times for head events are the same.


c)
The duration is equal to the head event time minus the tail event time.

The critical path is the longest path from start to finish, it has a zero float.

STEPS 7 AND 8 
ALLOCATE RESOURCES AND SMOOTH OUT THE NETWORK 


Scenario (Continued)

When the activity list was drawn up and the durations calculated, assumptions were made about staff availability.  It now transpires that only two instead of four people will be available to do activity 40 - Create data Files.  This means that activity will now take 15 weeks instead of 5.  

What effect does this have on the network? Re- draw your network.  Do you think the resulting situation would be tolerated?

STEP 9 
Check the network 

Your diagram may have ended up looking different from the one in the model answers.  The following exercise is more by way of guidance than a task.   Check back over your diagram and assure yourself that it is technically correct by using the following check-list: 

*
Avoid excessive detail if necessary draw a high level network with a series of low level diagrams for specific activities

*
Work through the network from finish to start checking for each activity "What had to be done before this?"

*
Work through the network from start to finish checking for each activity “What can be done now?"

*
Ensure that there is no looping
  or dangling
 

*
Ensure that each event is complete if all entering activities to the event are complete

*
An event must be unique; it must not appear more than once on the same network. All activities that are to do with that event must lead into or out of it directly or indirectly via dummy activities
 .

*
The sequence of arrows must not form a closed loop

*
Only one activity can be drawn between two events. If it is necessary to draw more than one activity between two events then add an additional event. 
SUMMARY
 Planning is not a precise technique and five different people are likely to come up with as many different plans for the same project.  Network analysis encourages a logical progression of thinking, analysis and planning.  Done in a cooperative manner it is an effective form of brainstorming.   Network analysis demands the application of common sense; it is not a difficult exercise. For networks to be effective they should be as simple and clear as possible 

Notes to Practical Tutors

Students should be able to work through this systematically; the only discussion is usually over dummy activities.  If students finish this in the practical I suggest that you ask one group to work through their solution.

� 	Looping is when it goes back onto itself into a continuous inescapable loop


� 	Dangling is when a task is going nowhere and is just left dangling in the air


� 	Dummy activities do nothing they show logical links between tasks there is an example of a dummy activity in the network shown, it is depicted by  a dotted line





Rosemary Phillimore 11/09/2006
Page 2 

